## Lead
Online Banking
Group Number - 4
Team Lead & Frontend Lead- Kathiresan x
Backend Lead - Stain Thomas Rajan Babu

## Status Track
Project Status Check Report Team - 4
Sl no. | Employee ID | Name | Domain | Module | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-11
1 | 2563068 | Boby Sebastian | Back-End, MicroServices | Saving Account Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server and have started working on Feign. | Completed Feign and have started working on Resilience4j. | Completed Resilience4j and Working on Sleuth and Zipkins | Completed the module and Combined all modules
2 | 2563662 | Joru Sandeep | Back-End, MicroServices | Register Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server and have started working on Feign. | Working on Feign. | Completed feign and working on resilience4j | Completed the module
3 | 2563935 | Kabilan M | Back-End, MicroServices | Login Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server | Working on Feign. | Completed feign and working on resilience4j | Completed the module
4 | 2564331 | Kathiresan X | Back-End, MicroServices | Account service, Admin service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server and have started working on Feign. | Completed Feign and have started working on Resilience4j. | Completed Resilience4j and Completed Sleuth and Zipkins | Completed the module and Combined all modules
5 | 2563523 | Niroop S Rao | Back-End, MicroServices | Transfer Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server and have started working on Feign. | Working on Feign. | Completed feign and working on resilience4j | Completed the module
6 | 2564006 | Shreya Ajit Kudachi | Back-End, MicroServices | Profile Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server and have started working on Feign. | Working on Feign. | Completed feign and working on resilience4j | completed the module and created the PowerPoint presentation.
7 | 2564059 | Stain Thomas Rajan Babu | Back-End, MicroServices | User History Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server and have started working on Feign. | Working on Feign. | Completed feign and working on resilience4j | Completed the module
8 | 2563078 | Thota Jayanth | Back-End, MicroServices | ChequeBook Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server . | Working on Feign. | Completed feign and working on resilience4j | Completed the module
9 | 2563432 | Vaishnavi Srivastava | Back-End, MicroServices | Loan Service | Discuss the project | Split the modules and started working on them. Also in the process of creating the database and setting up the server. | Created the configuration and Eureka Server and have started working on Feign. | Completed Feign and have started working on Resilience4j. | Completed Resilience4j and Completed Sleuth and Zipkins | completed the module and created the PowerPoint presentation.

## Status Meeting Group - Boby
Status Meeting Group - Boby Sebastian
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Joru
Status Meeting Group - Joru Sandeep
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Kabilan
Status Meeting Group - Kabilan M
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Kathir
Status Meeting Group - Kathiresan x
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Niroop
Status Meeting Group - Niroop S Rao
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Shreya
Status Meeting Group - Shreya Ajit Kudachi
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Stain
Status Meeting Group - Stain Thomas Rajan Babu
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Thota
Status Meeting Group - Thota Jayanth
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a

## Status Meeting Group - Vaishnav
Status Meeting Group - Vaishnavi Srivastava
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2023-09-05 |  |  |  |  | 16:00 | a
2023-09-06 | 10:00 | a |  |  | 16:30 | a
2023-09-07 | 10:00 | a |  |  | 16:30 | a
2023-09-08 | 10:00 | a | 14:00 | a | 17:20 | a
2023-09-09 | 10:00 | a | 14:00 | a | 16:30 | a
2023-09-11 | 10:00 | a |  |  | 16:30 | a